## Sheet1
Task | Description | Points | Num. People | Total Points | Assignees | Total Points |  | Calculated
Meeting 1 | Plan tasks, points, point distribution | 2 | 7 | 14 | All | 144 |  | 144
Meeting 2 | Review tasks, progress | 2 | 7 | 14 | All
Demo | Practice for retro | 1 | 7 | 7 | All
Review past sprint "future improvements" | Record in single place (let's use the discord thread or the readme) | 1 | 7 | 7 | All | Rashi | Sarah | Olivia | Mrudini | Burak | Cavaari | Jen
Misc. Documentation |  | 2 | 7 | 14 | All | 20 | 21 | 20 | 22 | 21 | 20 | 20
Update Individual About Pages | Prettier, accessibility | 2 | 7 | 14 | All
Testing |  | 4 | 2 | 8 | mrudini, sarah
Team Lead Tasks |  | 4 | 1 | 4 | jen
Fix Graph Limitations | colours | 3 | 2 | 6 | cavaari, jen
| hierarchy | 3 | 2 | 6 | burak, mrudini
| or nodes | 3 | 2 | 6 | cavaari, sarah
Site Dark Mode | Allow optional dark mode (involves accessiblity) | 4 | 2 | 8 | cavaari, burak
Planned Course List on Course Search Page | "add to plan" and download? kinda like https://cis3760f23-10.socs.uoguelph.ca/planner? | 3 | 2 | 6 | mrudini, jen
External Resources Page | Links to other UoG Resources | 2 | 1 | 2 | sarah
CI/CD? | Only with extra time | 2 | 2 | 4 | N/A
Remove prereqs from db Description |  | 2 | 1 | 2 | burak
Include unparsed prereqs in graph popups |  | 2 | 1 | 2 | burak
URI updates/changes |  | 2 | 2 | 4 | sarah, mrudini
Get courses from Major ("roadmap") | Design | 2 | 2 | 4 | rashi, olivia
| Select major -> get list of courses (Scrape from web page) | 4 | 2 | 8 | rashi, olivia
| Display: external resource, separate page, graph? | 4 | 2 | 8 | rashi, olivia